# Day 2 Find the Answer

Case study: ABC Retail real time order tracking release. The Friday release is at risk because client test environment access is still pending.

## 1 Find the answer

The release planned for Friday, 25 September, is at risk and may move to Monday, depending on when the client provides the required test environment access.

## 2 What changed

Testing has identified 18 defects; 14 have been fixed and retested, leaving four open. The environment access promised for Wednesday is still pending, creating a risk to the Friday release.

## 3 What is the problem

We cannot complete work on two defects related to the client’s existing order-management system because we lack access to the latest relevant test environment.

## 4 What is the impact

If access remains unavailable, we may be unable to complete fixes and validation in time for Friday. The release could move to Monday; the date is not yet confirmed.

## 5 What do you need

We need the client to provide access to the latest relevant order-management test environment and confirm exactly when that access will be available so we can resolve and retest the two blocked defects.

## 6 What happens next

Priya (Project Manager) will follow up with the client today to obtain test environment access and a confirmed availability time. Meanwhile, the development team will continue fixing the other two defects, which are expected to close by Thursday. Once access timing is known, the release date will be reassessed. The manager will receive the next status update by 10:00 AM tomorrow before the scheduled status call.

## 7 What information can you leave out

I would leave these details out of the first-line update:

The development work took place over the past two weeks.

Core functionality was completed on Monday and testing began on Tuesday.

The project manager discussed the situation with the technical lead.

- The 20 second update

Friday’s release is at risk and may move to Monday. Two defects are blocked by missing client test environment access, while the other two should close by Thursday. Priya (Project Manager) is following up with the client today to obtain access and confirm availability. The manager will receive the next update by 10:00 AM tomorrow, after which the release date will be reassessed.

Self check

Yes — I started with the release risk rather than the background.

Yes — I separated the main message from the supporting details.

Yes — I identified missing client test environment access as the blocker.

Yes — I explained the possible delay from Friday to Monday.

Yes — I made the request for access and a confirmed availability time clear.

Yes — the update is short enough to deliver in approximately 20 to 30 seconds.